## System-PAPP Status
Status Name | Name | Description | Status Date | Status Comments | Start | End | Functional Area | Sponsors
Approved (Not Started) | ITPC-0632 Outsource University Check Printing | Solicit bids for the University of Illinois System to outsource check printing and distribution operations to a vendor with industry expertise, redundant failover processes, business continuity assurances, and high-speed operations that can fulfill University stakeholder requirements. Outsourcing approved check files to an external vendor for maximum operational performance, business continuity, and providing this critical, essential service will improve the highly manual process used today and better leverage industry expertise and maximize University resource allocation for responsibilities that increase value. * Anticipated cost savings or cost neutral from equipment needs, paper supplies, reduced staff time and effort, and postage costs. * Transfers risks for continued operations of critical services, and recovery activities for issues to the vendor. * Shifts costs and liability to the vendor for ensuring end to end reconciliations and accuracy to eliminate printing errors such as damaged checks, missing checks, or duplicate checks. |  | Status remains- Will hold off on starting effort until other potential projects scope/goals are defined to determine if there is need for this effort. | November 2021 | June 2022 | Finance | Bill Patterson, Gloria Keeley
Approved (Not Started) | ITPC-0679 New page for GAR customers to make updates in Banner | University of Illinois annually bills 6,700 departmental customers for over $71 million in non-student receivables through General Accounts Receivable (GAR). University Bursar is requesting creation of a new GAR customer page in Banner Self-Service (alternative detailed in Section 15) for the 3,000 monthly GAR customers that would help facilitate self-service account maintenance functions as well as allow University Bursar to leverage our online billing and payment portal. The new page would allow GAR customers to login, review, and update account demographics: email(s), address(s) and phone number(s) utilizing currently available Banner APIs; replacing manual account updates. Additionally, GAR customers would be able to access UI-Pay, the University of Illinois System billing and payment platform, UI-Pay, to view their current bill, historical bills, make payments, sign up for payment plans and view real-time account details. Benefits: Currently many processes with GAR customers are manual and require effort from both University Bursar and a University Departments to maintain the accounts as well as provide account services. The new GAR self-service page would allow the University to utilize Banner provided APIs to automate the collection and maintenance of email addresses and billing addresses as the customer would have the access to updated themselves. Additionally, gaining access to UI-Pay would give the customers more services than are currently available. The customer would be able to see real-time information versus one day old. They would gain access to historical statements which are currently not available online and are only paper copies. They would be able to sign up for customized payment plans. Last, they would have the option for additional ways of paying like international wires. These improvements would increase ease of use for billing departments, departmental customers as well as improve revenue recognition and the billing cycle. The University would also be able to decommission an internal GAR payment portal, which struggles with technical support and updates. This would also reduce compliance risk surrounding e-checks and credit cards payments. |  | Project approved by ITPC and awaiting resources and outcome of two in-progress Bursar projects to determine which next Bursar projects will start. | June 2023 | November 2023 | Finance | Muna Bist
Approved (Not Started) | ITPC-0680 Streamline State Offset Process with new tables & form | University Bursar is requesting a new Banner table(s) and user interface form for the State of Illinois Offset Process. State Offset is a process required by Illinois state law in which the delinquent accounts are submitted to the state for the purpose of collections. As a state agency the University of Illinois is required to submit claims to the state comptroller on delinquent accounts that meet the specified criteria of having balance of $500 or more that is past due more than 60 days. Section 10.05 of the State Comptroller Act (15 ILCS 405/10.05) requires the Comptroller to deduct from warrants payable to any person the amount for which there exists a claim due and payable in favor of the state. Prior to submission of the claim, a warning letter must be sent to the debtor outlining the planned action and their rights to dispute the debt. After the warning letter is sent the debtor has 30 days to dispute the debt and/or request a hearing on the validity of the debt. Following the 30-day period, Bursar submits any non-disputed accounts with the comptroller and performs monthly maintenance on those accounts to keep balances up to date. The new table(s) would house all the data that is created by the University for the offset process, such as letter date, dispute date, offset submit date and Deduction order number along with the data created by the comptroller, such as IW Number, claim status, and update date. The table(s) would be updated by consuming standard feeder files from both the comptroller and Bursar as well as being editable via a Banner screen. Bursar would then utilize the new table(s) and screen to streamline the process for both students and staff by being able to see data in real-time. Benefits: Will eliminate the lag time between process updates for accounts. Will be more accessible to employees who can instantly access updated account data. Will eliminate the risk bad data or losing account information due to human error. Will improve data reliability being reported for quarterly report on State Offset which is being used in legal and audit purpose. Will eliminate the need for a middleware database and process, and the staff time dedicated to maintenance and upkeep, by incorporating the business data in Banner. |  | Changed On Hold Until from Nothing to Fri 1/31/25. Project approved by ITPC and awaiting resources and outcome of two in-progress Bursar projects to determine which next Bursar projects will start. | June 2023 | August 2023 | Finance | Muna Bist
Approved (Not Started) | ITPC-0684 Automate & track annual term-based detail codes process | University Bursar would like to automate our existing manual processing of Term-Based Details Codes. Each year, Bursar works with the 10 University departments to update the 650 term-based detail codes. The process is labor-intensive, using Banner screens to make copies of old records and then modify the records directly in Banner with details provided via email from the departments. Allowing for multiple points of user error. Additionally, departments will send the data to our office piecemeal leading to a long processing time. Additionally, we would like a BPI engagement to review the current process and determine the best direction forward. Benefits: Creating an online system for term-based detail code data to be processed through would allow for gathering concise term-based data up front, timely status feedback for requesting units, dashboard for each partnering unit to efficiently review term-based updates when it is their turn to review, streamlined C-FOAPAL interface with banner, automatic upload of a feeder, reduced manual errors, decrease overall timeline for all units involved. |  | Project approved by ITPC and awaiting resources and outcome of two in-progress Bursar projects. | June 2023 | December 2023 | Finance | Muna Bist
Approved (Not Started) | ITPC-0707 Integration strategy with iBuy & relevant dept systems | The university has been focused on making iBuy the centralized purchasing tool for the system. As we have gone through this process to integrate iBuy to Banner, we have identified shadow systems that are used for purchasing, accounting, and receiving. Upon further investigation, the use of shadow systems in conjunction with iBuy creates manual work for the related departments. By integrating these solutions, we plan to remove these manual efforts. We will conduct a proof-of-concept (POC) for this integration using two departments and two different shadow systems to verify this can be successful. We have selected Facilities Services at UIUC (F&S) and the Illini Union Bookstore and Retail Operations at UIUC to test the integration. The goal will be that the development work can be re-used for future areas interested in the integration to remove manual work. Expected Benefits: Eliminating significant time manually entering requisitions, purchase orders, and invoice data in respective systems. Improve data accuracy by leveraging electronic data vs. manually entered information. |  | Awaiting the implementation of digital mailroom. | August 2024 | March 2026 | Finance | Aaron Carter, Kelly Block, Maria Thompson, Tod Petrie, Brad Trankina
Approved (Not Started) | ESGC-0727 Automation of the Canadian Tax Request Form via Self-Service Sponsors | University Bursar would like to automate our existing manual processing of the Canadian tax form requests via Banner Self-Service. Each year Bursar creates the Canadian TILLA forms for the Canadian students who request the Canadian tax forms. The process is labor-intensive manual work which requires using Banner screens to extract the payment and registration details of all the students who request one. The process in which we intake the student can request the form from Bursar is also makeshift form in webtools in which students enter the form and Bursar staff needs to manually extract and verify the requests on a frequent basis. This doesn't have a seamless standardized process like the 1098T for domestic students. Additionally, other departments like registrar are involved in creating in some of the forms which have created redundancy and the possibility of incorrect reporting on payments and registration details from two different sources. The manual process includes having to: * Receiving the request forms either via webtool or from direct emails either from students or other departments. * Create a pdf with the student information for the registered terms, calculating the credit hours for the tax year, verifying with the students about the specific territory related forms. * This form process, unlike 1098T, doesn't have a fixed time frame, so, the forms can be requested throughout the year. University Bursar would like to create a process that would streamline the process via banner self-service by creating two different Canadian tax forms pdfs that can be filled with the information University provide whenever a student would like to access one. Benefits: Reduce manual errors and redundancy / Reduce the wait time for the student / Secure delivery system for the tax related documents of the students |  | XFG has approved this project and is ready to be reviewed at the scheduling meeting as soon as the documentation is completed. Need to determine the start date and resource needs. | June 2025 | November 2025 | Finance | Joe Shroyer
Approved (Not Started) | ESGC-0728 Rewrite of the State Clearing System (SCS) | The State Clearing System is essential for managing transactions and processing reimbursements tied to the University’s state appropriations. However, frequent system failures, including glitches, duplicate expenses, and job failures, cause delays and inefficiencies. This project will develop a modern, web-based system to improve efficiency, reduce errors, and streamline financial processes. Without these improvements, the University will continue to face financial risks, compliance challenges, and an increased burden on IT and accounting teams. Completing this project is critical to ensuring financial stability and operational efficiency. Benefits: Reduce financial risk / Reduce errors due moving to a web-based system, and improve the reimbursement process |  | XFG has approved this project and is ready to be reviewed at the scheduling meeting as soon as the documentation is completed. Need to determine the start date and resource needs. | August 2025 | February 2027 | Finance | John Laroe
In Process | SYS-0021 Facility Condition Assessment Investigation | The University of Illinois Urbana-Champaign (UIUC), the University of Illinois Chicago (UIC), and the University of Illinois Springfield (UIS) seek to embark on a system wide facility condition assessment (FCA). The FCA will provide a comprehensive evaluation of building systems, identify deficiencies and suggest and prioritize future repair or replacement needs. Building surveys will evaluate the general health of physical facilities by identifying and arranging inadequacies that require critical, urgent, and necessary remediation in alignment with risks associated with the inadequacies and their potential impact on life safety, continued building operation, and functionality. The appraisal will consider the age and serviceability of systems, components, and finishes of buildings to forecast replacement of facility assets as they reach the end of their serviceable life, as well as regular preventative maintenance impacts on expected replacement timelines. The objective of this investigation effort is to issue an RFP and based on responses determine next steps with the goal to identify a consultant to assist with the analysis and provide expertise on a software solution to track asset improvements and up-to-date condition reports. | 2025-07-07 13:49 | Changed Percent Complete from 90% to 94%. We still await the final draft of the report so that we can share it with university leadership. We are updating the current end date for the report is 9/30/25. | September 2022 | September 2025 | Capital Programs | Mike Wilson
In Process | ITPC-0708 Capital Programs’ Kahua Application Integrations and Reporting | The University Office of Capital Programs (UOCP) has been in the process of implementing Kahua to replace two software systems that currently provide project and financial management support to university capital construction units. This effort will implement reporting and needed integrations that were not able to be included in the initial July 2024 planned release. This is due to an accelerated timeline and functionality that was not determined to be available as we are implementing the Kahua product that will try to be addressed with a few focus areas in this project, if prioritized as such. Reporting functionality needs that are in place with PRZM and FCPWeb through the EDW will now need to come from Kahua. Establishing the connection and design of the new reporting tables/universe in the EDW are part of this project. Expected Benefits: Reduce or eliminate duplicative data entry ¦ Provide a more modern and streamlined technological solutions to common project management issues ¦ Allow for better reporting to be used or shared to manage all capital projects | 2025-07-10 10:25 | Initial requirements meetings for EDW/BI project are complete. The first phase for supplying 12 fiscal year end reporting extracts before 7/1/25 are complete and being utilized. EDW primary project analysis phase will begin in September. | January 2025 | May 2026 | Capital Programs | Nyle Bolliger, Mike Wilson
In Process | ITPC-0719 Degree Planning Portal utilizing curricular analytics (Phase 1) | The Degree Planning Portal will be a statewide tool to assist prospective students looking to transfer from academic institutions across Illinois to the University of Illinois Chicago (UIC). The portal will help transfer students from community colleges map out semester-by-semester pathways to degrees. It will also benefit high school and first-year students by allowing them to map out their degree pathways. This portal will integrate curricular analytics and degree audits to create a personalized, term-by-term degree map toward timely graduation. This map will then guide transfer and first-year students through their academic journey, helping them to understand all requirements for their desired baccalaureate degree program. Accessible via a website, the portal will provide information on the transferability of course credits from community colleges or high schools, thus maximizing the chances of completing an academic program in the minimum number of terms with minimal credit loss. Implementation of this tool will be a multi-phase effort, with the scope of the current phase (Phase 1) data extraction and development of the application front-end for students at UIC. This project will also prepare a plan for phase 2 of how to expand to the other universities in the system. Expected Benefits: Assist in the student onboarding process / Provide a clear plan and schedule to best achieve a degree in the student's desired program | 2025-07-09 11:17 | UIC is currently working with Damour to finalize Service and Licensing Agreements for the tool. The expectation is that these agreements will address Scope of Work, Schedule of Services, Security, and Existing IP. Team has been given verbal confirmation that we can expect to receive $500K in subawards from CPS and CCC as part of the Chicago Roadmap 2.0. We are awaiting written confirmation. Team has also submitted a full proposal that is in review status and moving along (just finalizing some follow-up questions with the program director). Team hopes to hear back from them soon. If successful, we’ve got an additional $200K in a budget line for the Degree Planning Portal (the tool). | November 2024 | November 2025 | DMA | Nikos Varelas, Amy Knetl, Nick Jones
In Process | ITPC-0699 Update BO universes to new format to continue support | SAP Business Objects is the supported enterprise reporting tool used at the University of Illinois. Business Objects Universes are used to deliver standard reports and ad-hoc reporting capabilities. SAP has deployed a new format, UNX, for the development of the BO Universes. SAP has developed plans to deprecate the legacy format, UNV. In order to be able to stay on supported versions of SAP Business Objects, all BO Universes have adhere to the new UNX format. The proposed timeline for deprecation by SAP is to end mainstream maintenance December 31, 2024. Before that date AITS will have upgraded to SAP Business Objects BI 2025. | 2025-07-09 10:29 | Changed Percent Complete from 50% to 55%. Phases 1-5 of the universe conversions have been completed. Phases 6 & 7 are now in progress and the team has identified universes for conversion for phases 8 & 9. The identified Unbound reports will be dealt with as the associated universes are migrated to avoid any unnecessary doubled work in this area. Team is Continuing to review documentation and communications with the SOSS Change Management team for all impacted users. | October 2023 | October 2025 | DMA | Dimuthu Tilakaratne, Mike Wonderlich
In Process | ITPC-0677 Improve Sharing & Collaboration with Data Lake Services | This project will implement an enterprise data lake service for use by data analysts. The effect is that data analysts will have a centralized data storage service that they can utilize instead of having to maintain or procure their own. The Microsoft Azure data storage solution will be used as the tool upon which the data lake service will be constructed. Processes and procedures to establish, maintain, and support the service will be defined during this effort. This includes governance, access and security, training, and support. Benefits: An enterprise data lake provides for better sharing and collaboration with data. Data analysts can store data in the data lake and utilize that data for analytics and reporting. This provides data analysts with the next generation data analytics capabilities necessary to provide the necessary information to University decision makers. Actionable insights available through better sharing and collaboration allow for better, informed decision making. | 2025-07-09 10:26 | Changed Percent Complete from 55% to 60%. Data lake connections from the web based fabric.Microsoft.com page are still not showing data lakes correctly. We are investigating this further. Jeff D. & Dean Dang working on multi-tenant solutions. Mike got Subscription Setup in UIC tenant for Dev Data Lake, planning to do same thing with UIS as long as this works. Power BI Pro for Dimuthu - Testing licensing and will go into sub to create capacity to get fabric up and running. Will then be able to test working between the two tenants. | July 2023 | October 2025 | DMA | Dimuthu Tilakaratne
In Process | ITPC-0645 Deliver improved financial data with FPPM Dashboard | The FPPM Dashboard will deliver improved financial information insight across the University of Illinois System. It will be used by University leadership, Budget Officers, Deans, Directors, Department Heads, Academic Fiscal Officers and Business Managers to monitor their financial process performance health in an informative and customizable format divided by actionable and informative items. The Dashboard will also be used by the CFO and system office staff to monitor the efficiency and effectiveness of financial processes and to offer support needs based on institutional risk. Dr. Ghosh has met with the project sponsors to confirm his support to offer financial process performance information in this format. The current iteration includes five metrics of actionable information and the Analysis team will interview key personnel in units, colleges, universities, and system offices to determine additional metrics and style options. The Dashboard and metrics were preliminarily vetted through various business staff to confirm both efficacy and value. Expected Benefits: By defining financial parameters and the data elements needed from disparate systems to appropriately measure financial process performance, day-to-day operations will be more focused efficient and effective. The Dashboard will enable the unit and college leadership to collaborate with system office staff in defining the data, access, and other Dashboard requirements so the product applies common definitions to parameters and improves process transparency. The Dashboard will highlight problematic process areas so education and resources may be applied which will in turn reduce state compliance audit findings. Additionally, savings will be realized as staff resources allocated to monitoring financial operations will become more efficient and will allow for resources to be used elsewhere. | 2025-06-30 11:51 | This project will be completed using multiple iterations of the Finance Process Performance Measures dashboard. The dashboard is embedded in My-UI-Financials application. The second iteration metrics requirements are progress. Once complete, logic updates will be incorporated into the dashboard source table, dashboard changes will begin. | August 2022 | December 2026 | Finance | Kelly Block, Brent Rasmus
In Process | ITPC-0593-E S2P Card Program Project | As Jaggaer does not offer a credit card purchase and payment mechanism, this effort is outside the scope of the iBuy Optimization. It is strategically important to assess the advantages and disadvantages of various card programs. It is also vital to identify an alternate solution to the existing PCard software which is at end of life. This request is for approval to complete the following: * Create a team to analyze the various uses of credit cards available as possible solutions to a variety of procure to pay needs * Investigate how credit card uses align with procurement strategy and the cost/benefit of deployment of the various identified possibilities. The team will consider cost savings due to reduced transaction costs as well as the ability to leverage the income that can be generated as the result of robust | 2025-07-08 18:52 | Decision has been made to change estimated completion date to 01/31/2026. Development of the CMP app continues but has been more than what was originally estimated. Testing continues with new scenarios as we near beginning to test the cardholder profile functionality. | January 2024 | January 2026 | Finance | James Martinie, Darren Strater
In Process | ITPC-0593-A S2P iBuy Optimization Project | Optimize the Jaggaer eProcurement module by taking advantage of functionality that has not been fully implemented, which may involve undoing system workarounds which were created by the University when the iBuy system was originally deployed. The eProcurement module incorporates requisition, catalog, and spend tracking functionality that should be leveraged. Work with Jaggaer and Ellucian to resolve issues related to the current integration method. Determine where the University may have deviated from Jaggaer’s standard configuration to facilitate upgrades, bug fixes, and ongoing maintenance. | 2025-06-11 09:58 | Changed Health from Yellow - At risk with corrective actions to Green - On track. Go live of Digital Mailroom was 05/15/25. Suppliers are being onboarded in waves, and we are continuing to work with third party invoice processor on invoices errors. Their performance will be monitored through mid-August to determine if we continue with Digital Mailroom or not. Payables is looking at every invoice to make sure errors are caught and corrected without disruption to departments and suppliers. But this is not sustainable long-term and due to concerns we have negotiated an evaluation period with the vendor. | July 2019 | October 2025 | Finance | Brent Rasmus Kelly Block
In Process | ITPC-0681 Automate billing process with new GAR Bill Banner table | University of Illinois produces over 37,000 GAR bills for 6,700 departmental customers for over $71 million each year. University Bursar is requesting a new Banner table to be built that would be populated by the Monthly GAR process, TFRBILL. The new table would allow Bursar to fully automate the billing process by containing all of the billing data inside Banner instead of just in a Banner lis file. The process and table would be a copy of the current setup utilized by the Monthly SAR bill process, TSRRBIL. The new table would be populated each month upon the TFRBILL process run and contain all appropriate data from the bill run, such as bill date, due date, statement number, address type and sequence number, total account balance, and total past due amount. Currently details of GAR bills are maintained only in the standard Banner lis files and pdf output of the process. Benefits: With a static bill table, Bursar can streamline processes related to the printing process of the GAR bills, being able to query addresses in realtime and create an automatic process to send files to print services based on addresses saving Bursar over 100 hours a year. Additionally, Bursar would be able to produce historical reports directly from Banner reporting sources such as REPTPROD. The table would help Bursar to research any questions related to GAR billing from a central location versus digging through Banner lis files. Last, The table would be a new resource for University departments to be able to review data provided to there customers through Banner GAR. | 2025-07-08 19:04 | After first run of GAR billing table for July reporting, we ran into some issues that we are troubleshooting to fix. Project close date is extended through 8/15 as this billing table is run once a month in production. | May 2024 | August 2025 | Finance | Muna Bist
In Process | ITPC-0682 Automate SAR bill format to reduce Bursar process time | University Bursar is requesting a new process to be built to create the monthly bill file submitted to our vendor NBS Quikpay. University Bursar is responsible for the monthly student billing of our 95,000 students. We utilize the built-in banner billing process, TSRRBIL, which uses the banner data to create the monthly billing statements for the students. This process then outputs a flat file that is uploaded to NBS QuikPay server for them to render the bills for the students. The process had previously been automatic with AITS running the process, encrypting the file and uploading to NBS Server. In recent years, the process has become manual as the baseline banner file contains errors. These errors stem from the banner data containing tab characters, multiple rows of city/Zip code, foreign characters, etc. The file now has to be manually reviewed each month to remove the issues before submitting to NBS. This has proved to be an obstacle in having an efficient billing process since the bill load process may sometime take multiple attempts when there is manual review of the flat file. To eliminate this billing process delay, the bill file needs to be reformatted in a Nelnet server acceptable format which won’t be rejected during the upload process. In addition, University Bursar wants to take this opportunity to improve a few other issues that have hindered the efficiency of billing. Specifically, NBS now allows for schools to send over the student email address as part of the bill file. This was eliminating a custom step that Bursar performs each month to obtain the email addresses of students not within NBS system and send a manual email blast. Therefore, University Bursar is looking to change the bill specs with additional information as well as build a customized parser that would clean the existing data fields being retrieved from the Banner for special characters and have them in appropriate format before uploading the file to the Nelnet server. This project would have a number of Benefits for Bursar and Students: Will help eliminate the upload failures to the Nelnet server. Will create an efficient monthly billing process by cutting down the processing time to one day instead of taking up to four days. Will automate the bill notifications to all come from NBS instead of a separate manual process from Bursar. | 2025-07-08 19:26 | Project team is working to define a clear process and specifications for transforming current LIS file data into Nelnet’s new required format. It was decided that parsing and format updates will be post-process (i.e., after LIS file is generated), without modifying the billing code itself. No change due to project team and stakeholders being out of office to answer questions. | March 2025 | November 2025 | Finance | Muna Bist
In Process | SYS-0027 iBuy Training Program​ | Based on recommendations from University Audits and in keeping with requirements already in place for Card Services, Journal Vouchers, and FABweb/Biennial, this project will create required training that must be completed prior to receiving Requestor or Approver access in iBuy. Introductory course(s) will be created and accessed through Ability LMS for Requestor and Approver profiles and the Security Application will be configured to query the Ability LMS tables for course completion when provisioning access for iBuy Requestor or iBuy Approver. Additionally, an ongoing training program will be developed to support iBuy users and help ensure they are following all applicable policies, procedures, and best practices. | 2025-06-30 08:41 | Then project team has created an issue log and we are currently working on building a Customer Advisory Group (CAG). We plan to have the CAG membership finalized by July 11 and then will work with the CAG to identify additional issues from the user perspective. | May 2025 | February 2026 | Finance | Brad Henson, Justin Johnston, Aaron Rosenthal​
In Process | ITPC-0674 HR/UPB updates due to new SURS Pension Admin System | SURS will be transitioning to a new Pension Administration System in the next 4 years. This will require significant modifications to existing business processes and systems. Human Resources (HR) and University Payroll & Benefits (UPB) will need to analyze current business processes, determine how they need modified and implement new policies and procedures to accommodate the new system. AITS will need to modify existing applications, files and reports for the various SURS components that exist today. In addition, there will be a need for new applications, files, and reports to meet the needs of the new SURS Pension Administration System. Expected Benefits: Faculty will have accurate reporting of SURS eligibility and benefits to SURS / Meet the requirements of the new system | 2025-07-07 16:34 | SURS has pushed the go-live date out one year to Feb/March 2028. | March 2023 | October 2028 | HR | Jami Painter, Cheri Canfield , Shari Mickey-Boggs, Melissa Mlynski, Larry Hanyzewski
In Process | SYS-0026 Implement Policy Database Software | In project SYS-0025 Research Policy Database Tools Research, we investigated available tools and systems to create a centralized database for all policies. We reviewed products from four different vendors and evaluated TeamDynamix and the KnowledgeBase as potential solutions. Onspring was the vendor selected, and we are now ready for purchasing and implementation. System Offices Shared Services (SOSS) and the Business and Finance Policy Office (Policy) will work with System Purchasing and Support Services to procure Onspring, and then work with AITS to configure the system. As part of this project, we will also formalize support for Onspring, which will be a shared responsibility between SOSS and Policy. | 2025-06-30 08:37 | We are still awaiting a completed contract, including language regarding accessibility remediations, to begin the implementation. In the meantime we are meeting with System Office units to better understand their policy needs. | February 2025 | July 2025 | Other | Karen Greenwalt
In Process | SYS-0024 Motor Vehicle Record (MVR) Ordering Process | The System needs to implement a process for ordering MVRs for “regular drivers” of university owned/leased vehicles. This is due to a new underwriting requirement from the System’s Excess Liability insurance carrier. The project includes determining the university’s definition of regular driver, identification of a method (vendor) for ordering the mvrs, procedure for reviewing mvrs, potential storing of PII, and development of process/policy for how adverse mvrs will be handled. | 2025-07-15 15:15 | Changed Percent Complete from 65% to 80%. The Motor Vehicle Report Policy has been finalized and approved. The committee is working with the vendor, HireRight, on the ordering and billing process. A pilot group of drivers has been identified and the goal is to start ordering MVRs on or before 8/1. A list of FAQs is being finalized and communications plans are being discussed. | June 2024 | August 2025 | Other | Tina Harlan, Shelly Romack
In Process | ESGC-0723 Purchase, Analyze and Implement Ellucian Intelligent Learning Platform | As we move towards a SaaS environment, we would like to continue taking advantage of the products and applications offered by Ellucian (our current ERP vendor.) In February 2024, we implemented Ellucian Experience. This is the platform that Ellucian is using to launch all of its new technology. We initially used it as a platform for entry into our Banner Self-Service applications, but there is untapped potential with Experience. One of the additional products being introduced by Ellucian is the Intelligent Learning Platform (ILP). This uses Experience to integrate the University’s Learning Management Systems (Blackboard for Chicago and Canvas for Urbana and Springfield) with Banner. | 2025-07-02 08:23 | On June 9, 2025, the team, in collaboration with UIS resources, initiated the setup of the test environment during a dedicated 6-hour working session. While the session was productive, there was some initial confusion regarding the scope and purpose of the project. To address this, a summary outlining the project's background was prepared and along with a separate document detailing its anticipated benefits. These documents were sent out to all stakeholders. The official project Kick-off meeting, originally planned earlier, has been rescheduled to July 8, 2025. In alignment with stakeholder feedback and to ensure campus-specific engagement, we have decided to conduct individual Kick-off meetings for each campus. The Project Charter has been updated with more information on benefits and will be distributed to project sponsors for approval within the week. | April 2025 | April 2027 | Student | Nyle Bolliger, Rod Hoewing, Drew MacGregor, Shannon Dwyer, Szymon Machajewski, Brian Catherwood, Kara McElwrath
In Process | ESGC-0725 Vended Application Testing and Remediation for ADA Title II Regulation Updates | The Department of Education has issued web accessibility regulations pursuant to Section 504 of the Rehabilitation Act, which prohibits discrimination in all public and private programs receiving federal financial assistance. This project will bring highly used AITS-developed applications into compliance with Federal Title II regulations. This project will bring AITS-supported vended applications into compliance with Federal Title II regulations. Expected Benefits: Ensure AITS-maintained vended applications compliant with the updated mandate / Improve accessibility of AITS-maintained vended applications for our faculty, staff, and students | 2025-07-09 21:55 | Changed Percent Complete from 20% to 30%. Have started conversation with SOSS on webpage that will link to (and be linked from) VPAA Accessibility website. The goal is to provide overall project updates and include stats on in-house applications and vended applications status and procedures. Working on sending procurement team round 4 and 5 vendors/applications for initial outreach letters. Continue to see responses come in from some vendors and updating list on vendors that need email for no response. Have some applications ear-marked for going through and testing the escalation process. Also working with AITS product owners to submit testing requests to QA for those vendors who have provided responses and VPAT info. | February 2025 | December 2029 | Technology | Nyle Bolliger; Jane Stone
In Process | ITPC-0620 Replace SecApp to improve access request / provisioning | This project’s purpose is to build, integrate, and deploy an AITS Security Application to replace the existing, homegrown product that has reached its limits of effectiveness and adoption at the University. The AITS ITPC-0584 Security Application Analysis project team completed a full examination of the current process and wrote user stories with requirements that aided in evaluation of a build or buy (vended) solution recommendation. The overall final recommendation to the University of Illinois AITS Leadership was to utilize the existing midPoint application architecture as a backend to meet the existing business needs and allow for additional functionality and future growth. Additionally, the recommendation included creating a governance structure and establishing standard processes for integration and adoption post-implementation as well as develop a training plan to assist in adoption of the new product. | 2025-07-02 08:39 | The team continues to make progress on the ARM Architectural Foundation Updates. UX efforts are ongoing, with work focused on updating front-end files for the Admin and Authorizer Inboxes, enhancing the View Access design—including navigation and accordion components—and verifying accessibility for both the Authorizer and Admin Inboxes. Additional UX tasks include implementing fixes on the Reconciliation page. On the development side, the team is simplifying the minor refractor and updating the refractor feature toggle service to support a distributed environment. Developers are also implementing design updates for the Authorizer Inbox and creating a new entitlement for the Banner WebTailor Role. Analysts are actively engaged in several areas, including the Banner Student UIC Profile Authorization setup and continued documentation of the Account Search page. They are also testing updates to the View Access and Admin Inbox designs. Additional analyst responsibilities include setting up EDW Student UIC and UIS Profile Authorizations, testing HR profiles delivered by developers, and evaluating both the Default Finance Profile and Banner Finance profiles. Analysts are collaborating with the appropriate Finance groups to ensure the Default Finance Profile is developed correctly and to finalize the language used to describe the profile and its settings. From a QA perspective, two testing tasks are scheduled to begin in the current sprint, supporting the broader development and implementation efforts. | August 2021 | March 2028 | Technology | Kelly Block, Karen McFarlin
In Process | ITPC-0605 Impl ITSM(IT Svc Mgt) and PPM(Proj Mgt) Cloud Solution | This project is to purchase, integrate, and deploy an enterprise ITSM and PPM Software as a Service (SaaS) private cloud solution to replace the existing, vended on-premise product that has reached its limits of effectiveness and adoption at the University. The ITSM Research Group, formed by the U of I IT Leadership Team, built criteria to analyze and evaluate vended solutions that could meet the University’s business needs and replace the existing solution. The ITSM Research Group provided a gap analysis, decision criteria evaluation, and overall final recommendation to the U of I IT Leadership Team that pointed to TeamDynamix as the selected vendor to meet existing business needs and allow for additional functionality and future growth. | 2025-07-09 22:17 | DS internal testing is complete for new EDW table and BO universe. User Acceptance Testing preparations are in progress. UAT will begin on 7/23. Proposed go live is 8/19. | October 2019 | December 2025 | Technology | Kelly Block, Cynthia Herrera Lindstrom,Tulio Llosa, Greg Gulick
In Process | SYS-0022 Analysis of potential Banking Disbursement Services RFP | Our current bank is BNY Mellon. We have been with them since 2006. Senior management has determined it to be beneficial to consider changing the incumbent bank, and review and evaluate alternative solutions and products that are available in the market. The primary goals of this effort are to solicit proposals relating to banking services for the following disbursement activities: University Payroll account to disburse payroll direct deposit (ACH) to university employees at all locations. University Payables disbursement account for general disbursement activity for the University including check, ACH. Student Refunds account to make ACH payments for student financial aid refunds. Funding account to facilitate the daily funding of disbursement activity for the accounts referenced above. Review and evaluate new services and products vendors may have to offer to improve efficiencies and operations of the System. Once it is determined what services a new banking service can offer based on the RFP output, we will decide what current processes could be impacted and what services we will be requesting from that new banking service. An implementation proposal will be submitted to PAPP and ITPC for the implementation of the new banking service as well as any new services or adjustments to current processes. | 2025-07-10 09:13 | Changed Percent Complete from 25% to 28%. Treasury is still working on the disbursement RFP and questions along with the evaluation grid. We have postponed our next meeting with System Purchasing to after Labor Day. | February 2023 | December 2025 | Treasury | Nichole Roberts, Sarah Crane
Completed | ITPC-0669 Replace aging Capital PM systems with a vended system | The University Office of Capital Programs (UOCP) seeks to replace two aging software systems that currently provide project and financial management support to university capital construction units. This project will lead to the retirement of PRZM and FCPWeb. Integrations with current peripheral softwares are being considered. This includes not only Banner but capital-centric systems such as AiM (work order system), VSA/CAPS (vendor maintenance system), and Contracts+ (contract creation and approval system). The Capital Enterprise Data Warehouse (EDW) will also be impacted as the majority of Capital data in the EDW is sourced from either PRZM or FCPWeb. The determination of whether or not the Capital EDW needs to be sourced from the new CPM application or if the CPM has sufficient reporting capabilities that a Capital specific EDW is no longer required will be made once a CPM system has been selected. Access to data exported from the system in a daily batch process is required. Note: An RFQ was issued in early 2022 and three vendors replied. UOCP is utilizing an outside consultant versed in project management-centric software solutions to help determine which is the best fit. This PAPP submission relates to the need to procure and configure the solution. Subsequent phases such as implementation and training will be added to the PAPP scope once determined. |  | Changed Status from In Process to Completed. This initial project focus plus additional scope added during project lifecycle are complete. There is a new project to address new scope and any additional efforts needed will be proposed and ran as individual projects. | January 2023 | June 2025 | Capital Programs | Mike Wilson
Completed | ITPC-0670-B Implement Data Virtualization - Logical Data Warehouse | Data virtualization provides the ability to virtually connect data from multiple locations and present it as one data source. This means that data can quickly and easily be accessed and integrated regardless of where it resides or how it is stored including database, APIs, files, etc. Data virtualization also provides capabilities to quickly curate data to meet specific analytics needs reducing the amount of data movement work needed. This results in easier and faster access to information which leads to enhanced decision making based on actionable insights. This effort will focus on the following: * Implement Denodo for data virtualization. * Deploy a logical data warehouse as the foundation for a data fabric. * Establish the data virtualization service. * Create a support model for assisting clients. * Create training to educate university data users on how to use the data virtualization service. |  | Changed Status from In Process to Completed. Project closing and Denodo Maintenance work will now be submitted under project: ESGC-0735 Maintain service to connect data from multiple locations. | August 2024 | July 2025 | DMA | Kelly Block , Nyle Bolliger, Dimuthu Tilakaratne
Completed | ITPC-0670-A Implement Data Virtualization to integrate data sources | Data virtualization provides the ability to virtually connect data from multiple locations and present it as one data source. This means that data can quickly and easily be accessed and integrated regardless of where it resides or how it is stored including database, APIs, files, etc. Data virtualization also provides capabilities to quickly curate data to meet specific analytics needs reducing the amount of data movement work needed. This results in easier and faster access to information which leads to enhanced decision making based on actionable insights. This effort will focus on the following: * Implement Denodo for data virtualization. * Deploy a logical data warehouse as the foundation for a data fabric. * Establish the data virtualization service. * Create a support model for assisting clients. * Create training to educate university data users on how to use the data virtualization service. |  | Changed Status from In Process to Completed. Project Implementation Completed, Additional work ongoing in Project: ITPC-0670-B | January 2023 | August 2024 | DMA | Kelly Block , Nyle Bolliger, Dimuthu Tilakaratne
Completed | ITPC-0683 Self-Service page for student access to sponsor data | University Bursar administers the Sponsor Billing program which bills approximately 3,500 students for $53 million across the three-campus system. Sponsor Billing is an arrangement a student will make with an outside organization, like their employer, to have their educational expenses paid. Bursar uses the baseline Banner processes to credit (pay) the students AR account and then charge the sponsors AR account in Banner, subsequently billing the sponsor for the student’s charges. The baseline Banner processing works very well but is missing some functionality for the students, mainly that students are unable to view the details that go into paying their student account. Bursar is requesting a new Banner Self-service page to be built that would display all the pertinent information to the students regarding their sponsorship. The page would include Sponsor account number, charges paid by the sponsor, Invoice numbers and remittance information from the Sponsor (see end of this document for a mockup). The new page would allow students to log into Banner self-service to review this information themselves instead of emailing Bursar staff. Additionally, the page could be made available through Proxy Access to appropriate staff to review the information. Benefits: With a self-service page for students, Bursar can reduce the number of emails and phone calls that are addressed to sponsor billing related to the status of a sponsorship. The reduction would free up our Sponsor Billing team to focus on communications with the Sponsor about the Invoices and payments due as well as work on any past due accounts. Additionally, the new page would help our frontline customer service team to field some additional questions as the information would be readily available. |  | Changed Status from In Process to Completed. The Student Self-Sponsor page is live in production and has been deployed to all students. If they have a sponsor, they will see the appropriate information. If not, they will not see anything. All students have the capability to remove the experience card from their homepage if they choose to do so. | May 2024 | January 2025 | Finance | Muna Bist
Completed | ITPC-0648 OBFS Website Redesign: Development & Implementation | This project will act on the analysis conducted during the phase-one project (SYS-0013) to create and test a final design for the new business and finance website, develop the site according to the design, and implement the site for user access and use. Benefits: 1. Focus the information that is displayed on business and finance subject areas and clearly align it with the CFO Office. 2. Confirm the scope of the topics and level of information that should be presented on the website as a result of the new organization structure and reflect the new relationships of organizations that have moved to the Universities. 3. Reface the website information to update the look and feel and improve navigation and search. |  | Project was completed successfully | April 2022 | March 2024 | Finance | Karen Greenwalt, Brent Rasmus, Kelly Block
Completed | ITPC-0649 Implement Internal control updates due to audit finding | Recently, internal audits uncovered several scenarios where University employees used access to multiple systems to conduct fraudulent transactions, using a multitude of purchasing and payment mechanisms and altering requests, invoices, and property accounting records as needed to avoid detection. In January 2019, a team of system and university experts in procurement, accounts payable, fixed assets, systems, and internal auditing were convened to perform an extensive analysis of system access roles and define the role combinations that present risk to the U of I System if duties are not appropriately separated. That analysis culminated in a final report that was completed in December 2019 with seven recommended long-term solutions, as well as some short-term solutions. The short-term scope has been completed and now we must move on to the long-term recommended solutions. Based on lessons learned during the short-term implementation project and given the large scope of the recommendations from the analysis team, we are recommending that the internal controls initiative be managed as a program. This approach will allow for greater coordination of the various components of the initiative, as well as increased flexibility and agile implementation of projects. Benefits: Address internal controls and segregation of duties discrepancies in the purchasing, payables, fixed asset, and systems access process. By addressing these items, progress towards deterring possibly fraudulent transactions can be shared with the Board of Trustees, external auditing agencies, and grant agencies as needed. This program will also ensure that an exception process will be implemented to allow units to continue processing necessary business transactions without unnecessary disruption. |  | Changed Status from In Process to Completed. Full scope of project completed successfully. | December 2021 | July 2024 | Finance | Brent Rasmus
Completed | SYS-0023 University Vehicle Accident Reporting Process Assessment | The University Vehicle Accident Reporting Process Assessment Project (herein referred to as “Assessment”) is a result of an ongoing State Compliance Audit finding related to Accident Reports testing. Specifically, the auditors have tested whether the University is in compliance with two benchmarks when an accident occurs in a university owned vehicle: (1) was the accident reported timely to CMS per the Illinois Administrative Code and (2) was the accident reported timely to the University per University policy. Several State Compliance Audit findings have been attributed to university noncompliance in accordance with this testing. The Assessment will examine the vehicle accident reporting structure implemented through policy and procedure at each of the three universities. The gathered information will then be utilized to determine whether a legislative change, change in State rules, or a change in University policy or procedure would assist in decreasing the number of State Compliance Audit findings in relation to this testing. The overall goal of this project is to improve the Vehicle Accident Reporting process to increase compliance under the State Compliance Audit. |  | Changed Status from In Process to Completed. The final report was presented separately to both Dr. Ellinger and the stakeholders. The project was completed by the beginning of May 2025 and Dr. Ellinger sent out the final charge letter to the stakeholders on June 11, 2025. | October 2023 | June 2025 | Finance | Bill Patterson, Ginger Velazquez
Completed | ITPC-0700 Commodity Codes clean-up for improved reporting | The Commodity Code Clean-up effort will consist of updating our current NIGP Commodity code listing and deleting/terminating outdated and user created codes. This effort will also include a change management effort based on creating new policies and procedures around proper use of the codes, as well as creating a system for review and approval of user codes that need to be added. |  | Changed Status from In Process to Completed. New NIGP commodity codes are now in Production. | January 2024 | January 2025 | Finance | Aaron Carter, Dan Szajna
Completed | ITPC-0625 FABweb Re-design and Biennial Inventory Enhancements | This project aims to improve the property accounting process and user experience for all University users. Upon project completion, new features and fixes will be introduced to FABweb, Biennial Inventory (BI), and the Surplus Warehouse Inventory System (SWIS). In addition some technologies utilized by UPAR will also be developed, so that all University users may be better supported. Benefits: Assist the department units in being more effective and identify and correct discrepancies in their equipment records ¦ Aid in reducing the University recurring negative audit findings related to equipment ¦ Assist by easing the burden on University faculty |  | Changed Status from In Process to Completed. Go-live successfully executed on 2/1/24 instead of 1/31/24, since 2/1 was a Thursday and a normal Change Control day. Production and Training environments updated to reflect functionality that was included in this ITPC. ITPC can be considered complete. | March 2021 | February 2024 | Finance | Brent Rasmus
Completed | SYS-0025 Research Policy Database Tools | Research available tools and systems to create a centralized database for all policies. Currently, policies are spread across various websites and managed in different ways. Our aim is to consolidate these into one central location for easier management and process flow, consistent updates, and efficient retrieval of historical information and current polices, especially for audit requests and as an accurate resource for the system. Internal departmental policies (i.e., governing internal office processes and policies) are currently outside the scope of this project. |  | Changed Status from In Process to Completed. Changed Health from Green to None. Full scope of work complete | June 2024 | January 2025 | Other | Karen Greenwalt